## Risk Log
ID | Risk | Category | Impact (1-5) | Likelihood (1-5) | Exposure (I x L) | RAG | Primary Mitigations / Controls | Contingency / Fallback Plan | Owner | Status | Review Cadence | Triggers / Early Indicators | Notes
1 | Insufficient Azure permissions to deploy resources | Governance/Access | 5 | 4 | 20 | High | Establish ADO service connection with OIDC; validate RBAC before pipeline run; use PIM for elevation; pre-flight 'what-if' stage | Escalate to subscription owner; run scoped deployment to resource group; defer non-critical components | DevOps Lead | Open | Weekly | RBAC 'AuthorizationFailed', 'Insufficient privileges' errors
2 | Limited platform team support / delays for SHIR VM or DNS linkage | Dependency | 4 | 4 | 16 | High | Agree RACI + SLAs; book change window; provide exact scriptable asks (VM image, subnet, DNS link) | Use temporary lab VM in hub; switch to Azure IR (Managed VNet) for internal tests if needed | Project Owner | Open | Weekly | Change tickets idle; no updates within agreed SLA
3 | DNS resolution fails across peering to client PG FQDN | Network/DNS | 4 | 3 | 12 | High | Validate private zone links from client to hub; fallback to Private DNS Resolver + forwarding; add DNS pre-flight in pipeline | Temporary host file override for PoC (lab only); engage client network team | Platform Network | Open | Weekly | nslookup fails on SHIR; ADF LS test shows name resolution error
4 | TCP 5432 blocked hub→client PG (NSG/Firewall) | Network/Security | 4 | 3 | 12 | High | Run TCP probe from SHIR subnet during pre-flight; share exact source IP ranges to client | Temporary rule exception during PoC window; reroute via approved jump network if available | Platform Network | Open | Weekly | Timeout during LS test; telnet/nc to 5432 fails
5 | UAMI not granted on client PG or AAD auth disabled | Identity/Database | 5 | 3 | 15 | High | Provide step-by-step grant; confirm AAD auth ON; include SQL to verify current_user in smoke test | Fallback to temporary SPN or DB user in KV (last resort, timeboxed) | Client DBA | Open | Weekly | Auth failed: SASL/AAD errors; 'role does not exist'
6 | Mismatch of PG major version / TLS settings causing connector errors | Compatibility | 3 | 3 | 9 | Medium | Capture PG version & SSL requirements; set sslmode verify-full where possible; test against a sample DB first | Relax to require TLS (verify-ca) for PoC; raise connector bug with Microsoft if reproducible | Data Eng Lead | Open | Weekly | Connector handshake/SSL errors in Script activity
7 | SHIR node unavailable during test (patch/reboot) | Operations | 3 | 3 | 9 | Medium | Deploy 2 nodes (N+1); enable auto-update; schedule change windows; health-check before run | Retry on other node; reschedule; temporarily allow Azure IR for read-only tests | Ops Lead | Open | Weekly | IR heartbeat alert; node status Down in ADF
8 | Agent version regression (v5.56+) impacts UAMI to PG | Software/Change | 4 | 2 | 8 | Medium | Record baseline version; enable auto-update but monitor release notes; have rollback package | Pin version temporarily; open ticket with Microsoft; switch to alternative runtime for tests | Ops Lead | Open | Weekly | New failures after agent auto-update
9 | Secrets exposure in pipeline logs or repo | Security | 5 | 2 | 10 | Medium | Use OIDC; store any non-AAD secrets only in Key Vault; mask variables; disable verbose logging for secret ops | Rotate impacted secrets; incident response playbook | Security | Open | Weekly | Plaintext creds in logs; secret scanning alerts
10 | Over-permissive RBAC for speed (privilege creep) | Security/Governance | 4 | 3 | 12 | High | Least-priv roles; time-bound PIM; peer review of role assignments; periodic access review | Back out broad roles; create custom role if needed | Security + DevOps | Open | Weekly | Owner role assigned to service principals; audit findings
11 | Change freeze or approval delays block schedule | Delivery/Governance | 3 | 3 | 9 | Medium | Publish plan with gates; pre-book CAB slots; keep PoC scope minimal | Resequence work (build ADF objects while infra waits); extend PoC window | Project Manager | Open | Weekly | CAB rejection or delay notices
12 | Pipeline agent capacity/unavailability in ADO | Platform/DevOps | 3 | 2 | 6 | Medium | Use Microsoft-hosted pool with demand-based parallelism; keep self-hosted agent as fallback | Switch pool; queue off-hours; temporarily run from local machine for unblock | DevOps Lead | Open | Weekly | Jobs stuck in queue; pool offline
13 | Unexpected cost from diagnostics/storage/log retention | Cost | 2 | 3 | 6 | Medium | Set retention to 30–90 days; filter noisy categories; use lifecycle policies in ADLS | Temporarily disable verbose categories; raise budget alert threshold | Project Owner | Open | Weekly | Budget alerts; steep cost deltas in daily report
14 | Azure quota/limit hit (e.g., cores for SHIR VMs) | Capacity/Quota | 3 | 2 | 6 | Medium | Pre-check quotas; request increases early; right-size VM size/region | Move workload to region with capacity; scale down temporarily | Platform Lead | Open | Weekly | QuotaExceeded errors during deployment
15 | Config drift between Dev and Prod ADF/IR objects | Release/Config | 3 | 3 | 9 | Medium | Git in Dev only; promote via CI/CD with parameter files; export ADF ARM for backup | Freeze manual edits; run drift detection; restore from export | DevOps Lead | Open | Weekly | Prod behaves differently; missing params on release
16 | Insufficient documentation/onboarding for client teams | Process | 2 | 3 | 6 | Medium | Provide runbook (grant UAMI, DNS link check, pipeline run); record PoC steps | Pairing session; support channel for first three client onboardings | Project Manager | Open | Weekly | Repeated questions; errors repeating across clients