## Plan
Phase | Task | Owner | Duration (days) | Start (day) | Finish (day) | Remarks | Depends On
1. Base services & identity | Create/validate ADO service connection & variable group | ADO Admin | 1 week |  |  | Can reuse the existing.
| Reserve names/tags; confirm hub RG(s) exist | Platform ¦ Data Eng |  |  |  | ADO pipeline work
| Create UAMI (uami-adf-dev) | Data Eng |  |  |  | ADO pipeline work
| Create Key Vault; add placeholder secret | Data Eng |  |  |  | ADO pipeline work
| Create ADLS Gen2 + 'logs' container | Data Eng |  |  |  | ADO pipeline work
| Assign RBAC: KV Secrets User to UAMI | Data Eng |  |  |  | ADO pipeline work | Create UAMI (uami-adf-dev)
| Assign RBAC: Storage Blob Data Contributor to UAMI | Data Eng |  |  |  | ADO pipeline work | Create UAMI (uami-adf-dev)
| Document outputs (KV URI, Storage URI, UAMI IDs) | Data Eng |  |  |  | Deliverable: Base Services Ready & Documented
2. Data Factory scaffold | Create ADF (adf-dev-<org>) | Data Eng | 1 week
| Attach UAMI to ADF identity | Data Eng |  |  |  | Create ADF (adf-dev-<org>) | Create ADF (adf-dev-<org>)
| Connect Git (Azure Repos) | Data Eng |  |  |  | Create ADF (adf-dev-<org>) | Create ADF (adf-dev-<org>)
| Enable diagnostics to Log Analytics (optional) | Data Eng |  |  |  | Create ADF (adf-dev-<org>) | Create ADF (adf-dev-<org>)
| Create SHIR logical runtime (shir-hub) in ADF | Data Eng |  |  |  | Create ADF (adf-dev-<org>) | Create ADF (adf-dev-<org>)
| Set ADF global parameters (kvUri, logContainer, shirName) | Data Eng |  |  |  | Create ADF (adf-dev-<org>) | Create ADF (adf-dev-<org>)
| Publish (baseline) | Data Eng |  |  |  | Connect Git (Azure Repos) | Connect Git (Azure Repos)
3. SHIR bring-up (hub) | Provision/identify SHIR VM(s) (Win 2022) in hub VNet | Platform | 1 week
| Install SHIR 5.56, register to 'shir-hub' | Platform ¦ Data Eng |  |  |  | Provision/identify SHIR VM(s) (Win 2022) in hub VNet | Provision/identify SHIR VM(s) (Win 2022) in hub VNet
| Enable auto-update; validate node(s) in ADF | Data Eng |  |  |  | Install SHIR 5.56, register to 'shir-hub' | Install SHIR 5.56, register to 'shir-hub'
| DNS test from SHIR (nslookup client PG FQDN) | Data Eng |  |  |  | Install SHIR 5.56, register to 'shir-hub' | Install SHIR 5.56, register to 'shir-hub'
| Connectivity test from SHIR (TCP 5432 to PG) | Data Eng |  |  |  | Install SHIR 5.56, register to 'shir-hub' | Install SHIR 5.56, register to 'shir-hub'
4. ADF objects & PoC | Create ADF Credential (ManagedIdentity → uami-adf-dev) | Data Eng | 1 week |  |  | Attach UAMI to ADF identity | Attach UAMI to ADF identity
| Linked Service: AzurePostgreSql v2.0 (UAMI, connectVia SHIR) | Data Eng |  |  |  | Create ADF Credential (ManagedIdentity → uami-adf-dev) | Create ADF Credential (ManagedIdentity → uami-adf-dev)
| Linked Service: Key Vault (for placeholder secret) | Data Eng
| Linked Service: ADLS Gen2 (optional, for logs) | Data Eng
| Pipeline: Script activity (SELECT current_user, version()) | Data Eng |  |  |  | Linked Service: AzurePostgreSql v2.0 (UAMI, connectVia SHIR) | Linked Service: AzurePostgreSql v2.0 (UAMI, connectVia SHIR)
| Publish & trigger run (client PG #1) | Data Eng |  |  |  | Pipeline: Script activity (SELECT current_user, version()) | Pipeline: Script activity (SELECT current_user, version())
| Optional: Write result to ADLS 'logs/' | Data Eng |  |  |  | Publish & trigger run (client PG #1) | Publish & trigger run (client PG #1)
| Create alert: pipeline failure; monitor IR heartbeat | Data Eng |  |  |  | Publish & trigger run (client PG #1) | Publish & trigger run (client PG #1)
| Document the SOP | Data Eng |  |  |  | Publish & trigger run (client PG #1) | Publish & trigger run (client PG #1)

## Phase Summary
Phase | Phase Duration (week)
1. Base services & identity | 1
2. Data Factory scaffold | 1
3. SHIR bring-up (hub) | 1
4. ADF objects & PoC | 1

## Decision Log
ID | Decision Area | Decision (Recommended) | Options Considered | Rationale | Owner | When to Decide | Status | Revisit Criteria | Notes
1 | Infrastructure as Code | Start with PowerShell for speed; prepare Terraform modules in parallel for long-term | PowerShell only ¦ Terraform only ¦ Hybrid (PS now ‚Üí TF later) | Fastest path to a PoC while paving a path to standardized IaC and state mgmt later | PO/TL | Now | Proposed | If constraints/assumptions change
2 | ADF Integration Runtime | Use SHIR (latest) ; reserve Azure IR for internal/MPE cases | SHIR only ¦ Azure IR (Managed VNet) ¦ Mixed | SHIR reaches many client PGs over existing peering; supports UAMI with PG v2.0 | PO/TL | Now | Proposed | If constraints/assumptions change
3 | ADF IR Deployment | SHIR VM can be considered currently, but need to revisit so that we can plan to deploy in k8s. | SHIR VM ¦ SHIR K8s | Deploying SHIR in k8s will allow to align with the UBS target computing platform | PO/TL | Now | Proposed | If constraints/assumptions change | k8s based IR is available and supports the ADF
4 | Network Model to Client PG | Use existing VNet peering; no MPE, no public IPs | Peering ¦ Managed Private Endpoints ¦ Public allowlist | Peering already in place; avoids per-client PE approvals and public exposure | PO/TL | Now | Proposed | If constraints/assumptions change
5 | PostgreSQL Auth | User-Assigned Managed Identity (UAMI) for Script activity | UAMI ¦ SPN (client secret/cert) ¦ DB user/password | Passwordless, centrally managed, least-privilege via Entra; aligns with zero-secret goal | DBA (Client) + Data Eng | Before first run | Proposed | If constraints/assumptions change
6 | DNS Resolution | Link client Private DNS zones to hub; fallback to Azure DNS Private Resolver | Zone linking ¦ Private Resolver + forwarding ¦ Hosts overrides | Most maintainable; keeps FQDNs intact; Private Resolver only if linking not possible | Platform + Client Network | Now | Proposed | If constraints/assumptions change | Its in place for existing ADF
7 | SHIR Topology | 2 nodes (N+1), auto-update on; scale-out if throughput requires | 1 node ¦ 2 nodes ¦ 3+ nodes | Resilience against single node failure; maintenance-friendly | PO/TL | Before SHIR install | Proposed | If constraints/assumptions change
8 | SHIR Hosts | Windows Server 2022, no public IP; patch via Update Mgmt; minimal egress | Public IP + RDP ¦ Bastion ¦ No public, JIT | Reduces attack surface; consistent with platform standards | PO/TL | Before SHIR install | Proposed | If constraints/assumptions change | If we proceed with SHIR VM
9 | ADF Source Control | Azure Repos; Git only in Dev; PR-based promotion to Test/Prod | Azure Repos ¦ GitHub ¦ No Git | Matches existing ADO; keeps prod clean and deploy-only | PO/TL | When creating ADF | Proposed | If constraints/assumptions change
10 | Release Strategy | Multi-stage YAML pipeline with environment approvals | Classic release ¦ Single-stage ¦ Multi-stage YAML | Traceable, reusable, easier approvals and conditions |  | Now | Proposed | If constraints/assumptions change
11 | Secrets Management | Key Vault/EVA for any non-AAD secrets; ADF references KV | Key Vault/EVA ¦ ADF secure strings ¦ Inline in code (avoid) | Centralized governance, rotation, and RBAC |  | Now | Proposed | If constraints/assumptions change
12 | Operational Logging | ADLS Gen2 per env; container 'logs' for pipeline results | Shared account ¦ Per-env accounts ¦ None | Clear isolation and lifecycle mgmt; cheap, simple evidence trail |  | Now | Proposed | If constraints/assumptions change
13 | Monitoring | Send ADF diagnostics to Log Analytics; alerts for pipeline failure & IR heartbeat | LAW + Alerts ¦ Storage logs only ¦ None | Actionable telemetry and alerting path for ops |  | After ADF creation | Proposed | If constraints/assumptions change
14 | PoC Test Pattern | Script activity ‚Üí Postgres LS (UAMI via SHIR); optional write to ADLS | Script Activity ¦ Function runner ¦ Copy-only ¦ Manual client tool | Directly validates UAMI + network; minimal moving parts |  | Now | Proposed | If constraints/assumptions change
15 | RBAC Model | Least-priv RBAC: scoped roles for UAMI; ADF Contributor for CI/CD; PIM for elevation | Broad Owner rights ¦ Least-priv + PIM ¦ Custom roles | Balance of security and operability; auditable changes |  | Now | Proposed | If constraints/assumptions change
16 | Naming/Tagging | Adopt corporate standard; include env, app, owner, cost center tags | Ad-hoc ¦ Corporate standard ¦ Minimal tags | Discoverability, cost mgmt, and policy compliance |  | Now | Proposed | If constraints/assumptions change
17 | Resilience/DR | Two SHIR nodes; idempotent infra scripts; ADF export for rebuild | Single node ¦ Multi-node + backups ¦ Active-active regions | Meets PoC RTO/RPO without overbuild |  | Now | Proposed | If constraints/assumptions change | Consider multi-region only if required later
18 | Approvals/Governance | Gates before SHIR install and first client run | No gates ¦ Single final gate ¦ Stage-level gates | Prevents accidental client impact; ensures prerequisites are met |  | Now | Proposed | If constraints/assumptions change
19 | Rollback Strategy | Idempotent scripts; what-if checks; manual approval before destructive ops | Ad-hoc reverts ¦ Full IaC with plans ¦ Script-based with guards | Reduces risk; makes changes predictable |  | Now | Proposed | If constraints/assumptions change
20 | DB Security Controls | Require SSL; enforce latest TLS; set sslmode verify-full where possible | Prefer TLS ¦ Allow non-SSL | Meets security baselines; reduces MITM risk |  | Before first run | Proposed | If constraints/assumptions change
21 | Component Versions | SHIR auto-update on; capture baseline; pin only if regressions occur | Auto-update ¦ Pinned version ¦ Mixed | Keeps patches current with low overhead |  | At SHIR install | Proposed | If constraints/assumptions change
22 | Audit Evidence | Store pipeline outputs & key logs in ADLS; 90-day retention (adjust per policy) | No retention ¦ Short-term ¦ Policy-aligned | Supports reviews and troubleshooting |  | After PoC run | Proposed | If constraints/assumptions change
23 | Private Endpoints (future) | Revisit PEs for Key Vault/Storage if clients standardize on PEs | No PEs ¦ PEs for all ¦ PEs selectively | Enhances isolation if operationally feasible later |  | Post-PoC | Deferred | If constraints/assumptions change

## Risk Log
ID | Risk | Category | Impact (1-5) | Likelihood (1-5) | Exposure (I x L) | RAG | Primary Mitigations / Controls | Contingency / Fallback Plan | Owner | Status | Review Cadence | Triggers / Early Indicators | Notes
1 | Insufficient Azure permissions to deploy resources | Governance/Access | 5 | 4 | 20 | High | Establish ADO service connection with OIDC; validate RBAC before pipeline run; use PIM for elevation; pre-flight 'what-if' stage | Escalate to subscription owner; run scoped deployment to resource group; defer non-critical components | DevOps Lead | Open | Weekly | RBAC 'AuthorizationFailed', 'Insufficient privileges' errors
2 | Limited platform team support / delays for SHIR VM or DNS linkage | Dependency | 4 | 4 | 16 | High | Agree RACI + SLAs; book change window; provide exact scriptable asks (VM image, subnet, DNS link) | Use temporary lab VM in hub; switch to Azure IR (Managed VNet) for internal tests if needed | Project Owner | Open | Weekly | Change tickets idle; no updates within agreed SLA
3 | DNS resolution fails across peering to client PG FQDN | Network/DNS | 4 | 3 | 12 | High | Validate private zone links from client to hub; fallback to Private DNS Resolver + forwarding; add DNS pre-flight in pipeline | Temporary host file override for PoC (lab only); engage client network team | Platform Network | Open | Weekly | nslookup fails on SHIR; ADF LS test shows name resolution error
4 | TCP 5432 blocked hub→client PG (NSG/Firewall) | Network/Security | 4 | 3 | 12 | High | Run TCP probe from SHIR subnet during pre-flight; share exact source IP ranges to client | Temporary rule exception during PoC window; reroute via approved jump network if available | Platform Network | Open | Weekly | Timeout during LS test; telnet/nc to 5432 fails
5 | UAMI not granted on client PG or AAD auth disabled | Identity/Database | 5 | 3 | 15 | High | Provide step-by-step grant; confirm AAD auth ON; include SQL to verify current_user in smoke test | Fallback to temporary SPN or DB user in KV (last resort, timeboxed) | Client DBA | Open | Weekly | Auth failed: SASL/AAD errors; 'role does not exist'
6 | Mismatch of PG major version / TLS settings causing connector errors | Compatibility | 3 | 3 | 9 | Medium | Capture PG version & SSL requirements; set sslmode verify-full where possible; test against a sample DB first | Relax to require TLS (verify-ca) for PoC; raise connector bug with Microsoft if reproducible | Data Eng Lead | Open | Weekly | Connector handshake/SSL errors in Script activity
7 | SHIR node unavailable during test (patch/reboot) | Operations | 3 | 3 | 9 | Medium | Deploy 2 nodes (N+1); enable auto-update; schedule change windows; health-check before run | Retry on other node; reschedule; temporarily allow Azure IR for read-only tests | Ops Lead | Open | Weekly | IR heartbeat alert; node status Down in ADF
8 | Agent version regression (v5.56+) impacts UAMI to PG | Software/Change | 4 | 2 | 8 | Medium | Record baseline version; enable auto-update but monitor release notes; have rollback package | Pin version temporarily; open ticket with Microsoft; switch to alternative runtime for tests | Ops Lead | Open | Weekly | New failures after agent auto-update
9 | Secrets exposure in pipeline logs or repo | Security | 5 | 2 | 10 | Medium | Use OIDC; store any non-AAD secrets only in Key Vault; mask variables; disable verbose logging for secret ops | Rotate impacted secrets; incident response playbook | Security | Open | Weekly | Plaintext creds in logs; secret scanning alerts
10 | Over-permissive RBAC for speed (privilege creep) | Security/Governance | 4 | 3 | 12 | High | Least-priv roles; time-bound PIM; peer review of role assignments; periodic access review | Back out broad roles; create custom role if needed | Security + DevOps | Open | Weekly | Owner role assigned to service principals; audit findings
11 | Change freeze or approval delays block schedule | Delivery/Governance | 3 | 3 | 9 | Medium | Publish plan with gates; pre-book CAB slots; keep PoC scope minimal | Resequence work (build ADF objects while infra waits); extend PoC window | Project Manager | Open | Weekly | CAB rejection or delay notices
12 | Pipeline agent capacity/unavailability in ADO | Platform/DevOps | 3 | 2 | 6 | Medium | Use Microsoft-hosted pool with demand-based parallelism; keep self-hosted agent as fallback | Switch pool; queue off-hours; temporarily run from local machine for unblock | DevOps Lead | Open | Weekly | Jobs stuck in queue; pool offline
13 | Unexpected cost from diagnostics/storage/log retention | Cost | 2 | 3 | 6 | Medium | Set retention to 30–90 days; filter noisy categories; use lifecycle policies in ADLS | Temporarily disable verbose categories; raise budget alert threshold | Project Owner | Open | Weekly | Budget alerts; steep cost deltas in daily report
14 | Azure quota/limit hit (e.g., cores for SHIR VMs) | Capacity/Quota | 3 | 2 | 6 | Medium | Pre-check quotas; request increases early; right-size VM size/region | Move workload to region with capacity; scale down temporarily | Platform Lead | Open | Weekly | QuotaExceeded errors during deployment
15 | Config drift between Dev and Prod ADF/IR objects | Release/Config | 3 | 3 | 9 | Medium | Git in Dev only; promote via CI/CD with parameter files; export ADF ARM for backup | Freeze manual edits; run drift detection; restore from export | DevOps Lead | Open | Weekly | Prod behaves differently; missing params on release
16 | Insufficient documentation/onboarding for client teams | Process | 2 | 3 | 6 | Medium | Provide runbook (grant UAMI, DNS link check, pipeline run); record PoC steps | Pairing session; support channel for first three client onboardings | Project Manager | Open | Weekly | Repeated questions; errors repeating across clients